## Active Sites
Site No. | GPS Coordinates | Site Name | Location | Description | Owner/leasee | Land Status | Site Work Completed/Planned | Comments | Priority
1 | 47.852648 N 122.541844 W | Hansville Landfill Plume | Landfill Plume | Evidence/knowledge of a large plume that extends from a former landfill to potentially near several neighborhoods on the Reservation | Tribe | Trust Land | Montioring Plan in place; track progress until contamination below cleanup levels | No further action needed as of now
2 | 47.87213705 N 122.54542017 W | Wrecking Yard | Private property Off Reservation | Old wrecking yard | Private property | Private Ownership | Phase 2 completed for Tribal lands adjacent to site; no contamination detected | Ecology potentially investigating
3 | Shoreline area between these coordinates: 47.84817462 N and 122.569743904 W and 47.85462168 N and 122.57276999 W | Car dump site | Between Gravel Plot Stairs and Bars | Car dump site | Tribe | Trust Land |  | Unstable bluff area, may not be suitable for cleanup | 4
4 | 47.836312 N 122.545761 W | Warrior Ridge Woods Area | Warrior Ridge Area | Back woods area that is accesed by a small access rd; large amounts of dumping evident (refrigerators; animal carcasses; trash) | Tribe | Trust Land | Outreach planned to prevent future dumping |  | 4

## Inactive Sites
Site No. | GPS Coordinates | Site Name | Location | Description | Owner/leasee | Land Status | Site Work Completed/Planned | Comments
1 | 47.824994 N 122.541844 W | Archery Range | 29299 Hansville Rd NE | Archery range Building | Tribe | Trust Land | Phase 1+2 completed; Site cleaned up by PGST | No further action needed
10 | 47.859465 N 122.568959 W | Old Wastewater Treatment Plant | Little Boston Rd. NE between Eaglewood Ln. NE and the skate park | Old wastewater treatment plant that is no longer used; outflow has experienced spills | Tribe | Trust Land | Phase 2 completed; detected no contamination |  | 1
1 | 47.85497681 N 122.57557269 W | Point Julia | At the end of Point Julia Road off Ne Boston Lane | Boating launch; fishing area; beach access | Tribe | Trust Land | Phase 1+2 completed; ABCA completed; debris removal completed; supplemented phase 2 detected no contamination |  | 1
2 | 47.85464387 N 122.57408740 W | Ancestral village site | On Point Julia | Ancestral village site | Tribe | Trust Land | Phase 2 ground penetrating radar and PAH sampling found no contamination |  | 1
3 | 47.85944627 N 122.56149208 W | Shooting area | Access Road off of Little Boston Road NE | Shooting Area in Back woods area | Tribe | Trust land | Outreach planned to prevent future dumping; Phase 2 completed; detected no contamination |  | 4
4 | 47.86159855 N 122.57303612 W | Bars | At the end of Boston Lane | Beach access area; evidence of dumping, illegal activies; concrete riprap of unknown origin | Tribe | Trust land | Phase 2 completed; detected no contamination. Concrete riprap does not contain asbestos |  | 3